## Schedule template
Date due | Task/action/product | Time/Location | Responsible party/parties & participants | Notes
TODO
TBD | Schedule meeting with the Liaisons
2017-08-25 | Initial questions for customer | 12 AM - 1 PM in B10 | Group lead, Customer liaison, & all
2017-08-25 | Management organization and responsibilities | 12AM - 1 PM in B10 | Group lead & all | Who are the various leads? What are their responsibilities? Is Doc lead responsible for updating schedule with new action items/tasks/milestones after each meeting? If not, who is?
2017-08-26 | Meeting with Sue | 11 AM - 2 PM in B10, Table 4 | All
2017-08-29 | Group Meeting | 2 PM - 4 PM in B10, Table 5 | All | DUE: 1. Questions for Liason 2. Introduction (30s - 1minute)
2017-09-01 | Review Code |  | Group/Arch leads, All | Review Documentation and Code from Last Year's Project (e.g. Database schema, iOS/Android, Azure Backend)
2017-09-01 | Download and Test Code |  | Phillip Han/Brian Kan (Android), Patricia Luz/Araceli Lopez (iOS), Sharon Lake/Daniel Bolligner (Backend) | Download and test Android/iOS projects on phone/emulator, Azure Backend
2017-09-01 | Refined questions/comments for customer at kickoff | 11 AM - 1 PM in Golden Eagle Ballroom | Group/Arch leads, Daniel Bollinger/Kaila Mayho | Are there any issues, e.g., apparent requirements that seem out of reach?
2017-09-02 | Group Meeting | 11 AM - 2 PM in B10, Table 4 | All
2017-09-08 | Work on Documentation and Requirements |  | Kaila, Araceli, Brian | Create a list of requirements and draft up a basic requirements document
2017-09-08 | Draft up a Basic UI Design for the Android App |  | Phillip and Daniel | Draft up UI ideas for the Android App
2017-09-08 | Draft up a DB Schema |  | Sharon and Patricia | Based on the details of the Liaison meeting, draft up a basic schema for the database
2017-09-08 | Project Plan (Meeting Minutes) | 12AM - 1 PM in B10 | Group lead & all | Where will documents and code be kept? (Google Drive & Github?) How will you do CM? When/where will you work together as a group each week? Other known milestones?
2017-09-09 | Group Meeting | 11 AM - 2 PM in Library | All
CURRENT TIME | 2018-05-08 11:50
2017-09-15 | Finish working on Documentation and Requirements |  | Kaila, Araceli, Brian | Finish up the Requirements Document
2017-09-15 | Implement the Android UI |  | Phillip and Daniel | Create a list of requirements and draft up a basic requirements document
2017-09-15 | Work with Android Team to implement Backend |  | Sharon and Patricia | Try and understand the backend logic for the Android App
2017-09-15 | Bug Testing/Fixing |  | Araceli Lopez | Test Android app and develop Bug List
2017-09-15 | Project Plan ( Meeting Minutes ) | 12AM - 1 PM in B10 | All
2017-09-16 | Group Meeting | 11 AM - 2 PM in Library | All
2017-09-18 | Liaison Meeting |  | Daniel Bollinger
2017-09-27 |  |  |  | 1. Categories/Subcategories 2. Hardware/Tablets 3. Bug List
2017-10-08 | QA Plan | 12AM - 1 PM in B10 | QA lead & all | Which testing/QA framework will you use? How will you run test suites automatically?
2017-10-15 | Personal Observations Essay - First Draft |  | Each person individually
2017-11-15 | Personal Observations Essay - Final Draft |  | Each person individually
2017-11-20 | Fall presentation slides |  | Group/Doc leads & all
2017-11-27 | Fall presentation |  | Group ensemble
2017-12-01 | Teamwork rubric |  | Each person individually
2018-12-05 | Requirements Document |  | Customer liaison, Doc lead, & all
2018-02-05 | Design Document |  | Arch/Doc leads & all
2018-03-01 | Lifelong Learning Essay First Draft |  | Each person individually
2018-04-01 | Lifelong Learning Essay Final Draft: |  | Each person individually
2017-05-01 | Poster |  | Doc lead & all
2018-05-04 | Expo slides |  | Group/Doc leads & all
2018-05-11 | Code |  | Arch lead & all
2018-05-11 | Expo |  | Group ensemble