## Sheet5
Milestone date | Project lead | Customer Liason | Documentation Lead | Android Lead | QA lead | Backend Lead | Architecture Lead
| Brian Kan | Daniel Bollinger | Kaila Mayho | Phillip Han | Araceli Lopez | Sharon Lake | Patricia Luz
CURRENT TIME | 2018-05-08 11:50
2017-08-25 | <- Initial questions for customer ->
2017-08-25 | Management organization and responsibilities
9/8/2017 Meeting Minutes | Setup Github/Slack/Google Drive/Project Page/Setup Meeting Time |  | Where will documents be kept? | Where will code be kept? | How will you do CM? | What will the schema be for the Azure database
9/15/2017 Meeting Minutes | Setup Meeting Minutes, Compiled Liaison Notes, established initial requirements | Contact liaisons on meeting time | Create a list of requirements and draft up a basic requirements document | Implement the Android UI | Test Android app and develop Bug List | Understand the backend logic for the Android App | Understand the backend logic for the Android App
9/22/2017 Meeting Minutes | Set up Dummy DB for Azure | Plan meeting in October with Liaisons | Finish Design Doc | Connect Android app to an actual Azure DB | Finished The Requirements Document | Understand the backend logic for the Android App | Understand the backend logic for the Android App
9/29/2017 Meeting Minutes | Fixed the Azure backend for the original app; Created a launchable URI for the app; Acquired Admin Credentials for SQL Database | Got credentials and set up a meeting with liaisons for 10/12 | Draft the requirements Draft | Attempted change to preferences but had to regress changes and store in broken branch. Reviewed code in preperation of implementing repair task id. Finished understanding Azure Classes. | Drafted The Requirements Document Draft | 1) draft wireframe completed, 2) connected via SSMS to both personal and BOE Azure instances to investigate the current underlying data structures, 3) created the tables in new database to test new schema to personal Azure instance | accessed the SQL database using SSMS and reviewed the relationship diagram of the current Azure SQL of PhotoArchive. Studied how SSMS works.
2017-10-06 | Setup Github integration Slack;Fixed up Requirements Document; History Tags now viewable via Long Press; Created a new account for Azure; | Contacted BOE and MS Azure to solve authorization issues. | Made changes to the Requirements Documentation Draft | Presentation on what's wrong with the current schema/application/ui; proposed changes; amount of work | Looked into Mockito Framework to see how to create unit test in Android Studio | Presentation on what's wrong with the current schema/application/ui; proposed changes; amount of work | Researched JUnit and Mockito for creating Test Cases.
2017-10-13 | Help Phillip implementing select images and replacing the textfield; optimizing the current code | Compile the list of information learned from the liaison | Proofread the Requirements Document. Implemented changes in the Design Document | Change select images;replace texfield for before and after with radio button | QA Plan. Which testing/QA framework will you use? How will you run test suites automatically? | Implement the repair task attribute/context | Work on writing/Designing Test cases and tests
2017-10-15 | Personal Observations Essay - First Draft. | Personal Observations Essay - First Draft. | Personal Observations Essay - First Draft. | Personal Observations Essay - First Draft. | Personal Observations Essay - First Draft. | Personal Observations Essay - First Draft. | Personal Observations Essay - First Draft.
2017-10-20 | Finish Optimizing the Code to reduce number of database calls | Got the categories/subcategories list from the Liaisons | Completed the Functional Requirements | Finalized settings page. Start UI changes on unstable branch. | Created a test plan. | Prepared a new database schema | Created a Test Plan Draft based from the requirements.
10/27/2017 Meeting Minutes | Revised Test plan, Decided that testing will be fragment-based | Installed the app on BOE-provided tablet and tested how the app scales to the larger size. Took notes on certain elements that should be changed and learned the technique for creating seperate tablet layouts. | Complete Design Document with pictures | Images tab | Adjusted the Test Plan based of last years project requirements | Create a new schema based on information liaisons | Learned Android Studio.
11/3/2017 Meeting Minutes | Worked on getting backend code to read the new schema changes | Found out A,B,U Permits are unique categories. Read the test plan and familiarized myself with Android testing strategies at Brian's suggestion. | Complete the Design Document based on last's progress & Adjusted Requirements Documents based on last week | Figure out how to add checkboxes and set fields as required or not required | Researched how to create unit test with Mockito framework and created a unit test. | Implement categories and subcategories that the liaisons provided | Studied Android Fragments and UI Testing with Espresso
11/10/2017 Meeting Minutes | Rewrote backend for Microsoft Azure server and uploaded to GitHub | Wrote unit tests with Robolectric, still trying to get them to work properly. Tested new version of app on tablet for UI changes. | Requirements Document & Presentation | Worked on Implementing Android ID instead of IMEI | Wrote unit tests with mockito and still trying to get them to work properly. | Worked on Fall Presentation. | created unit test for TabFragment5 but causes error every time shared preferences is called.
2017-11-15 | Personal Observations Essay - Final Draft | Personal Observations Essay - Final Draft | Personal Observations Essay - Final Draft | Personal Observations Essay - Final Draft | Personal Observations Essay - Final Draft | Personal Observations Essay - Final Draft | Personal Observations Essay - Final Draft
11/17/2017 Meeting Minutes |  | Worked on creating slides for powerpoint and preparing what to say during presentation | Added the Nonfunctional requirements. Continued to work on the presentation |  | Created slides for presentation and still trying to get the tests to work properly |  | Created an Instrumented Test for MainActivity. Also worked on the presentation.
2017-11-20 | Presentation slides
2017-12-01 | <- Fall presentation ->
2017-12-01 | Teamwork rubric | Teamwork rubric | Teamwork rubric | Teamwork rubric | Teamwork rubric | Teamwork rubric | Teamwork rubric
2018-12-05 |  |  | Requirements Document
2018-02-05 |  |  | Design Document
2018-03-01 | Lifelong Learning Essay First Draft | Lifelong Learning Essay First Draft | Lifelong Learning Essay First Draft | Lifelong Learning Essay First Draft | Lifelong Learning Essay First Draft | Lifelong Learning Essay First Draft | Lifelong Learning Essay First Draft
2018-04-01 | Lifelong Learning Essay Final Draft: | Lifelong Learning Essay Final Draft: | Lifelong Learning Essay Final Draft: | Lifelong Learning Essay Final Draft: | Lifelong Learning Essay Final Draft: | Lifelong Learning Essay Final Draft: | Lifelong Learning Essay Final Draft:
2017-05-01 |  |  | Poster
2018-05-04 | Expo slides
2018-05-11 |  |  | Documentation as deliverable package | Code as deliverable package
2018-05-11 | <- Expo ->